## Sheet1
Feature | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Hours Left | Settting | Start | 2023-03-13 | 2023-03-14 | 2023-03-15 | 2023-03-16 | 2023-03-17
User Registration Backend | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Planned Hours |  | 8 | 8 | 8 | 8 | 8
User Login Backend | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Actual Hours |  | 12 | 9 | 6 | 7 | 6
User Verification Backend | 3 | 0 | 3 | 0 | 0 | 0 | 0 | Remaining Effort | 40 | 28 | 19 | 13 | 6 | 0
User Search Movie Backend | 3 | 0 | 0 | 3 | 0 | 0 | 0 | Ideal Burndown | 40 | 32 | 24 | 16 | 8 | 0
User Get Movie Details Backend | 4 | 0 | 0 | 0 | 4 | 0 | 0
User Registration Frontend | 3 | 3 | 0 | 0 | 0 | 0 | 0
User Login Frontend | 3 | 3 | 0 | 0 | 0 | 0 | 0
User Verification Frontend | 3 | 0 | 3 | 0 | 0 | 0 | 0
User Logout Frontend | 3 | 0 | 3 | 0 | 0 | 0 | 0
User Search Movie Frontend | 3 | 0 | 0 | 3 | 0 | 0 | 0
User Get Movie Details Frontend | 3 | 0 | 0 | 0 | 3 | 0 | 0
User Load Backend | 3 | 0 | 0 | 0 | 0 | 3 | 0
User Load Frontend | 3 | 0 | 0 | 0 | 0 | 3 | 0