## Sheet1
Feature | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Hours Left | Settting | Start | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24
User Create Rating Backend | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Planned Hours |  | 8 | 8 | 8 | 8 | 8
User Read Rating Backend | 3 | 3 | 0 | 0 | 0 | 0 | 0 | Actual Hours |  | 12 | 12 | 4 | 9 | 0
User Update Rating Backend | 3 | 0 | 3 | 0 | 0 | 0 | 0 | Remaining Effort | 40 | 28 | 16 | 12 | 3 | 3
User Delete Rating Backend | 3 | 0 | 3 | 0 | 0 | 0 | 0 | Ideal Burndown | 40 | 32 | 24 | 16 | 8 | 0
Release Algorithm Design | 4 | 0 | 0 | 4 | 0 | 0 | 0
User Get Suggested Movies Backend | 3 | 0 | 0 | 0 | 3 | 0 | 0
User Get Prediction For A Movie Backend | 3 | 0 | 0 | 0 | 3 | 0 | 0
User Create Rating Frontend | 3 | 3 | 0 | 0 | 0 | 0 | 0
User Read Rating Frontend | 3 | 3 | 0 | 0 | 0 | 0 | 0
User Update Rating Frontend | 3 | 0 | 3 | 0 | 0 | 0 | 0
User Delete Rating Frontend | 3 | 0 | 3 | 0 | 0 | 0 | 0
User Get Suggested Movies Frontend | 3 | 0 | 0 | 0 | 3 | 0 | 0
User Get Prediction For A Movie Frontend | 3 | 0 | 0 | 0 | 0 | 0 | 3