## Sheet1
Feature | Initial Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Hours Left | Settting | Start | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31
Admin Login Backend | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Planned Hours |  | 8 | 8 | 8 | 8 | 8
Admin Get All Users Backend | 2 | 2 | 0 | 0 | 0 | 0 | 0 | Actual Hours |  | 10 | 8 | 8 | 6 | 6
Admin Get User Details Backend | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Remaining Effort | 40 | 30 | 22 | 14 | 8 | 2
Admin Delete User Backend | 2 | 0 | 2 | 0 | 0 | 0 | 0 | Ideal Burndown | 40 | 32 | 24 | 16 | 8 | 0
Admin Get All Movies Backend | 2 | 0 | 0 | 2 | 0 | 0 | 0
Admin Get Movie Details Backend | 2 | 0 | 0 | 2 | 0 | 0 | 0
Admin Add New Movie Backend | 2 | 0 | 0 | 0 | 2 | 0 | 0
Admin Delete Movie Backend | 2 | 0 | 0 | 0 | 0 | 2 | 0
User Get Prediction For A Movie Frontend | 2 | 0 | 0 | 0 | 0 | 0 | 2
Admin Login Frontend | 2 | 2 | 0 | 0 | 0 | 0 | 0
Admin Logout Frontend | 2 | 0 | 0 | 0 | 2 | 0 | 0
Admin Get All Users Frontend | 2 | 0 | 0 | 0 | 0 | 2 | 0
Admin Get User Details Details Frontend | 2 | 0 | 2 | 0 | 0 | 0 | 0
Admin Delete User Frontend | 2 | 0 | 2 | 0 | 0 | 0 | 0
Admin Get All Movies Frontend | 2 | 0 | 0 | 2 | 0 | 0 | 0
Admin Get Movie Details Frontend | 2 | 0 | 0 | 2 | 0 | 0 | 0
Admin Add New Movie Frontend | 2 | 0 | 0 | 0 | 2 | 0 | 0
Admin Delete Movie Frontend | 2 | 0 | 0 | 0 | 0 | 2 | 0
Admin Load Backend | 2 | 2 | 0 | 0 | 0 | 0 | 0
Admin Load Frontend | 2 | 2 | 0 | 0 | 0 | 0 | 0