## BLANK - Release Burn Up Chart
RELEASE BURN UP CHART
PROJECT TITLE |  |  | PROJECT MANAGER | START DATE | END DATE | OVERALL PROGRESS
Movie Recommendation System By Bot |  |  | Nguyen Minh Tien | 2023-03-06 | 2023-03-31 | 98%
TASK ID | KEY PROJECT TASKS | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
1 | User Authentication Management Backend | Complete | Nguyen Minh Tien | 2023-03-06 | 2023-03-10 | 5
2 | User Authenticate Management Frontend | Complete | Nguyen Minh Tien | 2023-03-06 | 2023-03-10 | 5
3 | Recommendation System Frontend | Approved | Nguyen Minh Tien | 2023-03-23 | 2023-03-31 | 9
4 | Recommendation System Backend | Complete | Nguyen Minh Tien | 2023-03-22 | 2023-03-23 | 2
5 | Rating Management Frontend | Complete | Nguyen Minh Tien | 2023-03-20 | 2023-03-23 | 4
6 | Rating Management Backend | Complete | Nguyen Minh Tien | 2023-03-20 | 2023-03-23 | 4
7 | Movie Management Frontend | Complete | Nguyen Minh Tien | 2023-03-08 | 2023-03-09 | 2
8 | Movie Management Backend | Complete | Nguyen Minh Tien | 2023-03-08 | 2023-03-09 | 2
9 | Admin Users Management Frontend | Complete | Nguyen Minh Tien | 2023-03-30 | 2023-03-31 | 2
10 | Admin Users Management Backend | Complete | Nguyen Minh Tien | 2023-03-30 | 2023-03-31 | 2
11 | Admin Movies Management Frontend | Complete | Nguyen Minh Tien | 2023-03-29 | 2023-03-30 | 2
12 | Admin Movies Management Backend | Complete | Nguyen Minh Tien | 2023-03-29 | 2023-03-30 | 2
13 | Admin Authenticate Management Frontend | Complete | Nguyen Minh Tien | 2023-03-27 | 2023-03-30 | 4
14 | Admin Authenticate Management Backend | Complete | Nguyen Minh Tien | 2023-03-27 | 2023-03-30 | 4
15
16
17
18
19
20
BURN UP CHART

## Dropdown Keys - Do Not Delete -
DROPDOWN KEYS
YES / NO | PRIORITY | STATUS
Yes | Low | Not Started
No | Medium | In Progress
| High | Complete
| Must do | Needs Review
Approved
Overdue
On Hold